## Project Plan Template
PROJECT INVOICE MANAGEMENT
| PROJECT TITLE |  | START DATE
| INVOICE MANAGEMENT |  | 2024-07-20 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
|  |  | 2024-10-27 |  |  | 100
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT DEFINITION AND PLANNING | In Progress |  | 2024-07-20 | 2024-07-30 | 11 |  | Not Started
1.1 | – Objective | Complete |  | 2024-07-20 | 2024-07-30 |  |  | In Progress
1.1.1 | –– Design a web for invoice management that can upscalable | Complete |  | 2024-07-20 | 2024-07-30 |  |  | Complete
1.2 | – Target Audience | Complete |  | 2024-07-20 | 2024-07-30 |  |  | On Hold
1.2.1 | –– Using for company | Complete |  | 2024-07-20 | 2024-07-30
1.3 | – Core feature | Complete |  | 2024-07-20 | 2024-07-30
1.4 | – Technology stacks | Complete |  | 2024-07-20 | 2024-07-30
2 | ARCHITECTURE DESIGN | In Progress |  | 2024-07-30 | 2024-08-30 | 32
2.1 | –Api Design | In Progress |  | 2024-07-30 | 2024-08-20 | 22
2.1.1 | –– User Api (Login/Register, CRUD ) | Complete |  | 2024-07-30 | 2024-08-20
2.1.2 | –– Role Api(CRUD) | Complete |  | 2024-07-30 | 2024-08-20
2.1.3 | –– Privilege Api(CRUD) | Complete |  | 2024-07-30 | 2024-08-20
2.1.4 | –– Invoice Api(CRUD) | Complete |  | 2024-07-30 | 2024-08-20
2.1.5 | –– Vendor Api(CRUD) | Complete |  | 2024-07-30 | 2024-08-20
2.2 | – DATABASE DESIGN | In Progress |  | 2024-07-30 | 2024-08-20 | 22
2.1.1 | –– User | Complete |  | 2024-07-30 | 2024-08-20
2.1.2 | –– Role | Complete |  | 2024-07-30 | 2024-08-20
2.1.3 | –– Privilege | Complete |  | 2024-07-30 | 2024-08-20
2.1.4 | –– Invoice | Complete |  | 2024-07-30 | 2024-08-20
2.1.5 | –– Vendor | Complete |  | 2024-07-30 | 2024-08-20
2.3 | – UI/UX DESIGN | In Progress |  | 2024-02-04 | 2024-02-12 | 9
2.1.1 | –– Login/Register | In Progress |  | 2024-07-30 | 2024-08-20
2.1.2 | –– User | In Progress |  | 2024-07-30 | 2024-08-20
2.1.3 | –– Role | In Progress |  | 2024-07-30 | 2024-08-20
2.1.4 | –– Privilege | In Progress |  | 2024-07-30 | 2024-08-20
2.1.5 | –– Invoice | In Progress |  | 2024-07-30 | 2024-08-20
2.1.6 | –– Vendor | In Progress |  | 2024-07-30 | 2024-08-20
2.3 | – UI/UX DESIGN | In Progress |  | 2024-02-04 | 2024-02-12 | 9
3 | PROJECT LAUNCH & EXECUTION | Complete |  | 2024-02-18 | 2024-03-26 | 38
3.1 | – Status & Tracking | In Progress |  | 2024-02-18 | 2024-02-20 | 3
3.2 | – KPIs | In Progress |  | 2024-02-18 | 2024-02-23 | 6
3.2.1 | –– Monitoring | In Progress |  | 2024-02-18 | 2024-02-26 | 9
3.2.2 | –– Forecasts | Not Started |  | 2024-02-21 | 2024-02-23 | 3
3.3 | – Project Updates | Not Started |  | 2024-02-22 | 2024-02-23 | 2
3.3.1 | –– Chart Updates | In Progress |  | 2024-02-25 | 2024-03-26 | 31
4 | PROJECT PERFORMANCE / MONITORING | In Progress |  | 2024-02-25 | 2024-03-26 | 31
4.1 | – Project Objectives | In Progress |  | 2024-02-25 | 2024-02-28 | 4
4.2 | – Quality Deliverables | On Hold |  | 2024-02-26 | 2024-03-03 | 7
4.3 | – Effort & Cost Tracking | Not Started |  | 2024-02-25 | 2024-03-06 | 11
4.4 | – Project Performance | Not Started |  | 2024-03-03 | 2024-03-26 | 24
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Project Plan Template
PROJECT PLAN TEMPLATE
| PROJECT TITLE |  | START DATE
PROJECT DURATION
| PROJECT MANAGER |  |  |  |  | in days
1
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION |  |  |  |  | 1 |  | Not Started
1.1 | – Project Charter |  |  |  |  | 1 |  | In Progress
1.1.1 | –– Project Charter Revisions |  |  |  |  | 1 |  | Complete
1.2 | – Research |  |  |  |  | 1 |  | On Hold
1.3 | – Projections |  |  |  |  | 1
1.4 | – Stakeholders |  |  |  |  | 1
1.5 | – Guidelines |  |  |  |  | 1
1.6 | – Project Initiation |  |  |  |  | 1
2 | PROJECT DEFINITION AND PLANNING |  |  |  |  | 1
2.1 | – Scope & Goal Setting |  |  |  |  | 1
2.2 | – Budget |  |  |  |  | 1
2.3 | – Communication Plan |  |  |  |  | 1
2.4 | – Risk Management |  |  |  |  | 1
3 | PROJECT LAUNCH & EXECUTION |  |  |  |  | 1
3.1 | – Status & Tracking |  |  |  |  | 1
3.2 | – KPIs |  |  |  |  | 1
3.2.1 | –– Monitoring |  |  |  |  | 1
3.2.2 | –– Forecasts |  |  |  |  | 1
3.3 | – Project Updates |  |  |  |  | 1
3.3.1 | –– Chart Updates |  |  |  |  | 1
4 | PROJECT PERFORMANCE / MONITORING |  |  |  |  | 1
4.1 | – Project Objectives |  |  |  |  | 1
4.2 | – Quality Deliverables |  |  |  |  | 1
4.3 | – Effort & Cost Tracking |  |  |  |  | 1
4.4 | – Project Performance |  |  |  |  | 1
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.